## Version Control
Wi-Finder
Requirements Traceability Matrix

Submitted to:	Ma. Rowena C. Solamo
	Faculty Member
	Department of Computer Science
	College of Engineering
	University of the Philippines, Diliman

Submitted by:	Miguel Luis G. Posadas
	Juan Gabriel C. Tamayo
	Zechariah B. Jimenez

In partial fulfillment of Academic Requirements
for the course
CS 191 Software Engineering
1st Sem AY 2014-2015

History Revision:

Revision Date	Person Responsible	Version Number	Modification
Oct 4	Zechariah Jimenez	1.0	Original Document
Oct 4	Miguel Posadas	1.1	Correction of prototype status
Jan 20	Zechariah Jimenez	2.0	Addition of Backlog
Mar 13	Zechariah Jimenez	3.0	Backlog Update post-Sprint 3

## Requirements
RTM ID	Description	Priority Status	Has Prototype?
Use Case 0.0	System should be able to launch on a mobile platform	Should Have	no
Use Case 1.0	System should be able to update local database	Must Have	yes
Use Case 1.1	System should be able to search the local database	Must Have	yes
Use Case 2.0	System should be able to implement a system for reporting wi-fi	Should Have	no
Use Case 3.0	System should be able to detect if device is connected to wi-fi	Could Have	no
Use Case 4.0	System should be able to rate and comment on wi-fi	Must Have	no
Use Case 4.1	System should be able to rate on wi-fi	Must Have	yes
Use Case 4.2	System should be able to comment on wi-fi	Should Have	no

## Backlog
Use Case No.	Description	Story Points	Value Points	BFTB
1.1	System should be able to search the local database	8	34	4.25
4.1	System should be able to rate the wi-fi	21	89	4.2380952381
4.2	System should be able to comment on the wi-fi	5	21	4.2
1.0	System should be able to update local database	34	144	4.2352941176
0.0	System should be able to launch on a mobile platform	55	211	3.8363636364
2.0	System should be able to implement a system for reporting wi-fi	13	55	4.2307692308

Sprint	Description	Use Case	Story Points	Expected Velocity	Actual Points	Actual Velocity
1	System should be able to update local database	1.0	34	63	0	5
	System should be able to search the local database	1.1	8		5
	System should be able to rate the wi-fi	4.1	21		0
2	System should be able to search the local database	1.1	8	29	8	21
	System should be able to rate the wi-fi	4.1	21		13
3	System should be able to rate the wi-fi	4.1	21	60	21	45
	System should be able to comment on the wi-fi	4.2	5		3
	System should be able to update local database	1.0	34		21
4	System should be able to comment on the wi-fi	4.2	5	39		0
	System should be able to update local database	1.0	34